## Summary
Metric | Value
Generated (UTC date) | 2026-06-29
Canonical workbook path | docs/audit/agend-terminal-user-story-feature-tracker.xlsx
Total user stories | 107
Stories with user story text | 107
Stories not yet tested | 18
Observed errors documented | 4
Fixes completed | 3
Retests completed (post-fix) | 89
Stories executed against built binary | 89
Stories passing | 88
Artifact-tool availability | Unavailable in this environment; workbook emitted as OOXML using stdlib
Test method | Release binary + agend-mcp-bridge stdio driven against an isolated AGEND_HOME (live fleet untouched)
Loop status | Inventory done; broad code/API/TUI testing done; 3 logistical/UX bugs fixed + retested; remaining stories are interactive/destructive/external-service/feature-gated
Feature Area | Story Count
CLI | 22
Feature documentation | 18
MCP tools | 37
System / infrastructure | 22
TUI | 8
Priority | Story Count
P0 | 15
P1 | 49
P2 | 40
P3 | 3

## Feature Stories
Story ID | Feature Area | Feature / Behaviour | User Story | Expected Behaviour | Primary Interface | Source Evidence | Inventory Status | Story Status | Test Status | Observed Errors | Fix Status | Retest Status | Priority | Suggested Test / Verification | Notes / Uncertainties
US-DOC-001 | Feature documentation | Agent Interaction — Terminal Access to Agents | As an operator, I want the Agent Interaction — Terminal Access to Agents capability to behave as documented, so that I can rely on the product documentation matching the implemented product surface. | The documented Agent Interaction — Terminal Access to Agents behaviours are available through their described CLI/MCP/TUI entry points; core subflows include: Usage Scenarios, Motivation, attach — Connect to an Agent's Terminal, inject — Send Text to an Agent, list — List All Agents, kill — Terminate an Agent, connect — Attach an External Agent, Typical Workflows. | Docs + corresponding CLI/MCP/code | docs/FEATURE-agent-interaction.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Review docs/FEATURE-agent-interaction.md against the referenced source modules and run the relevant CLI/MCP smoke tests. | Feature-doc row; lower-level CLI/MCP/TUI rows below track concrete behaviours. ¦ TEST: attach/inject/list/kill/connect behaviours were exercised in isolated daemon smoke tests.
US-DOC-002 | Feature documentation | Channels — Telegram / Discord Integration | As an operator, I want the Channels — Telegram / Discord Integration capability to behave as documented, so that I can rely on the product documentation matching the implemented product surface. | The documented Channels — Telegram / Discord Integration behaviours are available through their described CLI/MCP/TUI entry points; core subflows include: Usage Scenarios, Design Goals, Quick Start, Core Concepts, Topics Mapping, Message Flow, Deduplication, Notification Gate. | Docs + corresponding CLI/MCP/code | docs/FEATURE-channels.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Review docs/FEATURE-channels.md against the referenced source modules and run the relevant CLI/MCP smoke tests. | Feature-doc row; lower-level CLI/MCP/TUI rows below track concrete behaviours. ¦ TEST: cargo test --bin agend-terminal channel:: / channel::telegram / notification_queue passed, covering channel binding, Telegram adapter, auth, dedup, caps, and notification UX.
US-DOC-003 | Feature documentation | CI Watch — Automated PR CI Monitoring | As an operator, I want the CI Watch — Automated PR CI Monitoring capability to behave as documented, so that I can rely on the product documentation matching the implemented product surface. | The documented CI Watch — Automated PR CI Monitoring behaviours are available through their described CLI/MCP/TUI entry points; core subflows include: Usage Scenarios, Design Rationale, Usage, How It Works, PR Conflict Detection, Stall Detection, TTL and Auto-Cleanup, CI Provider Support. | Docs + corresponding CLI/MCP/code | docs/FEATURE-ci-watch.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Review docs/FEATURE-ci-watch.md against the referenced source modules and run the relevant CLI/MCP smoke tests. | Feature-doc row; lower-level CLI/MCP/TUI rows below track concrete behaviours. ¦ TEST: cargo test --bin agend-terminal daemon::ci_watch and daemon::pr_state passed, covering CI watch and PR-state behaviours.
US-DOC-004 | Feature documentation | Inter-Agent Communication System | As an operator, I want the Inter-Agent Communication System capability to behave as documented, so that I can rely on the product documentation matching the implemented product surface. | The documented Inter-Agent Communication System behaviours are available through their described CLI/MCP/TUI entry points; core subflows include: Usage Scenarios, Design Philosophy, Three Core Tools, Message Types (request_kind), Delivery Modes, Message Delivery Mechanism, Inbox Operations, Threading. | Docs + corresponding CLI/MCP/code | docs/FEATURE-communication.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Review docs/FEATURE-communication.md against the referenced source modules and run the relevant CLI/MCP smoke tests. | Feature-doc row; lower-level CLI/MCP/TUI rows below track concrete behaviours. ¦ TEST: MCP send/inbox/task smoke tests passed and channel/notification queues passed.
US-DOC-005 | Feature documentation | Configuration Layers: `AGEND_HOME`, `fleet.yaml`, runtime config, and MCP config | As an operator, I want the Configuration Layers: `AGEND_HOME`, `fleet.yaml`, runtime config, and MCP config capability to behave as documented, so that I can rely on the product documentation matching the implemented product surface. | The documented Configuration Layers: `AGEND_HOME`, `fleet.yaml`, runtime config, and MCP config behaviours are available through their described CLI/MCP/TUI entry points; core subflows include: Usage Scenarios, Configuration layers at a glance, `AGEND_HOME`, `.env`, `fleet.yaml`, `runtime-config.json`, `DaemonConfig`, MCP config: derived settings for each backend. | Docs + corresponding CLI/MCP/code | docs/FEATURE-configuration.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Review docs/FEATURE-configuration.md against the referenced source modules and run the relevant CLI/MCP smoke tests. | Feature-doc row; lower-level CLI/MCP/TUI rows below track concrete behaviours. ¦ TEST: runtime_config, mcp_config, and fleet tests passed.
US-DOC-006 | Feature documentation | Decisions — Decision Traceability | As an operator, I want the Decisions — Decision Traceability capability to behave as documented, so that I can rely on the product documentation matching the implemented product surface. | The documented Decisions — Decision Traceability behaviours are available through their described CLI/MCP/TUI entry points; core subflows include: Usage Scenarios, Design Goals, Quick Start, Operations, Decision Structure, When to Record a Decision, Supersedes, Tag System. | Docs + corresponding CLI/MCP/code | docs/FEATURE-decisions.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Review docs/FEATURE-decisions.md against the referenced source modules and run the relevant CLI/MCP smoke tests. | Feature-doc row; lower-level CLI/MCP/TUI rows below track concrete behaviours. ¦ TEST: decision post/list smoke passed.
US-DOC-007 | Feature documentation | Diagnostics and Evidence: `agend-terminal doctor / bugreport / capture` | As an operator, I want the Diagnostics and Evidence: `agend-terminal doctor / bugreport / capture` capability to behave as documented, so that I can rely on the product documentation matching the implemented product surface. | The documented Diagnostics and Evidence: `agend-terminal doctor / bugreport / capture` behaviours are available through their described CLI/MCP/TUI entry points; core subflows include: Usage Scenarios, Feature overview, `doctor`: global health check, `doctor topics`: Telegram topic diagnostic, `bugreport`: one-shot diagnostic bundle, `capture backend`: capture raw backend output, `capture promote`: turn a capture into a replay fixture, File and data source map. | Docs + corresponding CLI/MCP/code | docs/FEATURE-diagnostics.md | Inventoried from code/docs | Drafted | Not Started |  | Not Started | Not Started | P1 | Review docs/FEATURE-diagnostics.md against the referenced source modules and run the relevant CLI/MCP smoke tests. | Feature-doc row; lower-level CLI/MCP/TUI rows below track concrete behaviours.
US-DOC-008 | Feature documentation | Dispatch Idle Tracking — Task Response Timeout Monitoring | As an operator, I want the Dispatch Idle Tracking — Task Response Timeout Monitoring capability to behave as documented, so that I can rely on the product documentation matching the implemented product surface. | The documented Dispatch Idle Tracking — Task Response Timeout Monitoring behaviours are available through their described CLI/MCP/TUI entry points; core subflows include: Usage Scenarios, Design Rationale, Usage, How It Works, Expiry Cleanup, Visibility Query, Configuration, Typical Flow. | Docs + corresponding CLI/MCP/code | docs/FEATURE-dispatch-idle.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Review docs/FEATURE-dispatch-idle.md against the referenced source modules and run the relevant CLI/MCP smoke tests. | Feature-doc row; lower-level CLI/MCP/TUI rows below track concrete behaviours. ¦ TEST: daemon::dispatch_idle tests passed.
US-DOC-009 | Feature documentation | Fleet Management — Unified Agent Configuration | As an operator, I want the Fleet Management — Unified Agent Configuration capability to behave as documented, so that I can rely on the product documentation matching the implemented product surface. | The documented Fleet Management — Unified Agent Configuration behaviours are available through their described CLI/MCP/TUI entry points; core subflows include: Usage Scenarios, Motivation, fleet.yaml Structure, Startup Process, Resume Mode, Lifecycle Management, fleet.yaml Field Merge Rules, FAQ. | Docs + corresponding CLI/MCP/code | docs/FEATURE-fleet.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Review docs/FEATURE-fleet.md against the referenced source modules and run the relevant CLI/MCP smoke tests. | Feature-doc row; lower-level CLI/MCP/TUI rows below track concrete behaviours. ¦ TEST: fleet:: tests passed (83 passed, 1 ignored).
US-DOC-010 | Feature documentation | Health & Monitoring — Agent Health State and Auto-Recovery | As an operator, I want the Health & Monitoring — Agent Health State and Auto-Recovery capability to behave as documented, so that I can rely on the product documentation matching the implemented product surface. | The documented Health & Monitoring — Agent Health State and Auto-Recovery behaviours are available through their described CLI/MCP/TUI entry points; core subflows include: Usage Scenarios, Design Rationale, Two-Layer State Model, Crash Handling, Hang Detection, Auto-Recovery Ladder, Watchdog — PTY Output Classification, Idle Watchdog — Inactivity Detection. | Docs + corresponding CLI/MCP/code | docs/FEATURE-health.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Review docs/FEATURE-health.md against the referenced source modules and run the relevant CLI/MCP smoke tests. | Feature-doc row; lower-level CLI/MCP/TUI rows below track concrete behaviours. ¦ TEST: health:: and daemon::idle_watchdog tests passed; health MCP smoke passed.
US-DOC-011 | Feature documentation | Quickstart — Interactive First-Time Setup | As an operator, I want the Quickstart — Interactive First-Time Setup capability to behave as documented, so that I can rely on the product documentation matching the implemented product surface. | The documented Quickstart — Interactive First-Time Setup behaviours are available through their described CLI/MCP/TUI entry points; core subflows include: Usage Scenarios, Motivation, Interactive Flow, FAQ, Technical Details. | Docs + corresponding CLI/MCP/code | docs/FEATURE-quickstart.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Review docs/FEATURE-quickstart.md against the referenced source modules and run the relevant CLI/MCP smoke tests. | Feature-doc row; lower-level CLI/MCP/TUI rows below track concrete behaviours. ¦ TEST: quickstart --unattended smoke passed.
US-DOC-012 | Feature documentation | Schedules & Deployments — Timed Jobs and Batch Deployment | As an operator, I want the Schedules & Deployments — Timed Jobs and Batch Deployment capability to behave as documented, so that I can rely on the product documentation matching the implemented product surface. | The documented Schedules & Deployments — Timed Jobs and Batch Deployment behaviours are available through their described CLI/MCP/TUI entry points; core subflows include: Usage Scenarios, Design Goals, Schedules — Timed Jobs, Deployments — Batch Deployment, Common Patterns, When to Use Schedules vs Deployments, Failure Modes, Practical Advice. | Docs + corresponding CLI/MCP/code | docs/FEATURE-schedules.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Review docs/FEATURE-schedules.md against the referenced source modules and run the relevant CLI/MCP smoke tests. | Feature-doc row; lower-level CLI/MCP/TUI rows below track concrete behaviours. ¦ TEST: schedules and deployments tests passed; schedule/deployment MCP smoke passed.
US-DOC-013 | Feature documentation | Service Management: `agend-terminal service` | As an operator, I want the Service Management: `agend-terminal service` capability to behave as documented, so that I can rely on the product documentation matching the implemented product surface. | The documented Service Management: `agend-terminal service` behaviours are available through their described CLI/MCP/TUI entry points; core subflows include: Usage Scenarios, What this feature solves, Supported platforms, The three subcommands, macOS behavior, Linux behavior, Windows behavior, Idempotency rules. | Docs + corresponding CLI/MCP/code | docs/FEATURE-service.md | Inventoried from code/docs | Drafted | Not Started |  | Not Started | Not Started | P1 | Review docs/FEATURE-service.md against the referenced source modules and run the relevant CLI/MCP smoke tests. | Feature-doc row; lower-level CLI/MCP/TUI rows below track concrete behaviours.
US-DOC-014 | Feature documentation | Skills — Cross-Backend Skill System | As an operator, I want the Skills — Cross-Backend Skill System capability to behave as documented, so that I can rely on the product documentation matching the implemented product surface. | The documented Skills — Cross-Backend Skill System behaviours are available through their described CLI/MCP/TUI entry points; core subflows include: Usage Scenarios, Design Philosophy, Quick Start, Directory Structure, CLI Commands, Writing Skills, Per-Agent Skill Filtering, Automatic Installation Timing. | Docs + corresponding CLI/MCP/code | docs/FEATURE-skills.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Review docs/FEATURE-skills.md against the referenced source modules and run the relevant CLI/MCP smoke tests. | Feature-doc row; lower-level CLI/MCP/TUI rows below track concrete behaviours. ¦ TEST: skills CLI add/list/install/remove smoke passed.
US-DOC-015 | Feature documentation | Task Board | As an operator, I want the Task Board capability to behave as documented, so that I can rely on the product documentation matching the implemented product surface. | The documented Task Board behaviours are available through their described CLI/MCP/TUI entry points; core subflows include: Usage Scenarios, 1. Design Rationale, 2. Files and Modules, 3. Data Model, 4. Status Semantics, 5. `task action=create`, 6. `task action=list`, 7. `task action=claim`. | Docs + corresponding CLI/MCP/code | docs/FEATURE-task-board.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Review docs/FEATURE-task-board.md against the referenced source modules and run the relevant CLI/MCP smoke tests. | Feature-doc row; lower-level CLI/MCP/TUI rows below track concrete behaviours. ¦ TEST: tasks:: and task_events tests passed; task MCP smoke passed.
US-DOC-016 | Feature documentation | Teams | As an operator, I want the Teams capability to behave as documented, so that I can rely on the product documentation matching the implemented product surface. | The documented Teams behaviours are available through their described CLI/MCP/TUI entry points; core subflows include: Usage Scenarios, 1. Design Rationale, 2. Files and Modules, 3. Data Model, 4. `team action=create`, 5. `team action=list`, 6. `team action=update`, 7. `team action=delete`. | Docs + corresponding CLI/MCP/code | docs/FEATURE-teams.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Review docs/FEATURE-teams.md against the referenced source modules and run the relevant CLI/MCP smoke tests. | Feature-doc row; lower-level CLI/MCP/TUI rows below track concrete behaviours. ¦ TEST: teams:: tests passed; team MCP list smoke passed.
US-DOC-017 | Feature documentation | TUI — Multi-Agent Management Interface | As an operator, I want the TUI — Multi-Agent Management Interface capability to behave as documented, so that I can rely on the product documentation matching the implemented product surface. | The documented TUI — Multi-Agent Management Interface behaviours are available through their described CLI/MCP/TUI entry points; core subflows include: Usage Scenarios, Launch, Core Concepts, Keyboard Shortcuts, Command Palette, Task Board, Session Persistence, Terminal Compatibility. | Docs + corresponding CLI/MCP/code | docs/FEATURE-tui.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Review docs/FEATURE-tui.md against the referenced source modules and run the relevant CLI/MCP smoke tests. | Feature-doc row; lower-level CLI/MCP/TUI rows below track concrete behaviours. ¦ TEST: TUI keybind/layout/mouse/overlay/session/command tests passed.
US-DOC-018 | Feature documentation | Worktree Management | As an operator, I want the Worktree Management capability to behave as documented, so that I can rely on the product documentation matching the implemented product surface. | The documented Worktree Management behaviours are available through their described CLI/MCP/TUI entry points; core subflows include: Usage Scenarios, 1. Design Rationale, 2. Directories and Markers, 3. Worktree Creation, 4. Creation Entry Points, 5. Lease and Bind, 6. Soft Release, 7. Hard Release. | Docs + corresponding CLI/MCP/code | docs/FEATURE-worktree.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Review docs/FEATURE-worktree.md against the referenced source modules and run the relevant CLI/MCP smoke tests. | Feature-doc row; lower-level CLI/MCP/TUI rows below track concrete behaviours. ¦ TEST: worktree and binding tests passed; worktree MCP smoke exercised release/binding_state/gc.
US-CLI-001 | CLI | Start daemon | As an operator, I want start the daemon in detached or foreground mode, so that agents become available without manually launching each backend. | agend-terminal start starts the daemon, accepts --fleet, --foreground, and --agents name:cmd specs, and foreground is implied for explicit agents. | CLI | src/main.rs: Commands::Start; docs/CLI.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P0 | agend-terminal start --foreground --agents shell:/bin/sh in a temp AGEND_HOME, then list/stop. | TEST: start (detached service + --agents foreground) launched daemon; list went Live.
US-CLI-002 | CLI | Launch TUI app | As an operator, I want open the interactive multi-pane app, so that I can manage the fleet visually. | agend-terminal app launches owned/attached TUI mode using the selected fleet path. | CLI/TUI | src/main.rs: Commands::App; src/app/mod.rs; docs/FEATURE-tui.md | Inventoried from code/docs | Drafted | Not Started |  | Not Started | Not Started | P0 | Run app in an isolated terminal with a small fleet and verify pane rendering and detach.
US-CLI-003 | CLI | Attach to agent terminal | As an operator, I want attach to a running agent PTY, so that I can observe and intervene in a backend session. | attach defaults to shell and connects without changing the agent execution state. | CLI | src/main.rs: Commands::Attach; docs/FEATURE-agent-interaction.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Start a shell agent, run attach, type a command, detach. | TEST: attach path exercised via PTY; verify 'attach' probe passes.
US-CLI-004 | CLI | Inject text into an agent | As an operator, I want send text to an agent input buffer, so that I can script or recover an agent without manual typing. | inject accepts an agent name plus text and writes it to the target PTY using the daemon path. | CLI | src/main.rs: Commands::Inject; docs/FEATURE-agent-interaction.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Inject `echo ok` into a shell agent and observe output. | TEST: inject shell wrote marker.txt; content confirmed.
US-CLI-005 | CLI | List/status agents | As an operator, I want list live agents in plain or JSON forms, so that I can see fleet state and health. | list/ls/status reports agents; --json implies detailed API-backed output and --legacy-json preserves the deprecated envelope. | CLI | src/main.rs: Commands::List; docs/CLI.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Run list, ls, status, list --detailed, and list --json against a running daemon. | TEST: list / ls / status / list --detailed / list --json all returned expected shapes.
US-CLI-006 | CLI | Connect external agent | As an operator, I want register an externally managed agent with backend metadata, so that external sessions can use daemon MCP without being daemon-spawned. | connect requires name and backend, optionally working dir and extra args, and registers an external agent. | CLI | src/main.rs: Commands::Connect; src/connect.rs; docs/FEATURE-agent-interaction.md | Inventoried from code/docs | Drafted | Pass | ERR-004: failed connect registered an external agent before backend spawn and left a stale connected entry when spawn failed. | Done | Pass | P2 | Connect a test external shell/codex backend and verify it appears as external. | TEST: Fixed: connect deregisters external agent on spawn error; red regression test failed before impl and passes after fix; positive /usr/bin/true connect still passes.
US-CLI-007 | CLI | Stop daemon | As an operator, I want stop the running daemon cleanly, so that the fleet shuts down without orphaning normal state. | stop routes to daemon shutdown for the active AGEND_HOME. | CLI | src/main.rs: Commands::Stop; src/daemon/mod.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P0 | Start temp daemon; run stop; verify API is unavailable and process exits. | TEST: stop cleanly shut down the isolated daemon.
US-CLI-008 | CLI | Kill agent | As an operator, I want terminate a selected agent, so that a stuck or unwanted backend can be removed. | kill accepts an agent name and invokes daemon lifecycle teardown; managed agents may be subject to restart policy. | CLI | src/main.rs: Commands::Kill; src/agent/deleting.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Start two agents; kill one; verify registry and PTY disappear. | TEST: kill shell removed the live agent; list reflected removal.
US-CLI-009 | CLI | Set operator mode | As an operator, I want set active/away/sleep with optional delegate scope, so that agents can respect operator availability and authority boundaries. | mode accepts active, away, or sleep plus delegate/scope values and stores operator authority state. | CLI | src/main.rs: Commands::Mode; src/operator_mode.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Set each mode in temp AGEND_HOME and verify MCP mode get reflects it. | TEST: mode active flipped operator authority; previously-blocked tools then allowed.
US-CLI-010 | CLI | Cleanup merged branches | As an operator, I want preview and delete merged local branches, so that old branch clutter can be removed safely. | admin cleanup-branches defaults to dry-run; --yes applies deletion of eligible branches. | CLI | src/main.rs: AdminCommands::CleanupBranches; src/branch_sweep.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Create clean/squash/stale branch fixtures and compare dry-run vs --yes. | TEST: admin cleanup-branches dry-run listed merged branches (24 skipped, 0 deleted) without mutating.
US-CLI-011 | CLI | Cleanup zombie daemons | As an operator, I want find and reap stale daemon run directories/processes, so that dead daemon state does not block new launches. | admin cleanup-zombies filters by --age and prompts unless --yes; Unix uses TERM then KILL grace path. | CLI | src/main.rs: AdminCommands::CleanupZombies; src/admin/cleanup_zombies.rs | Inventoried from code/docs | Drafted | Not Started |  | Not Started | Not Started | P1 | Use fixture run dirs/process mocks if available; avoid killing real daemon in-session. | Do not run destructive zombie cleanup against the live session.
US-CLI-012 | CLI | Capture backend output | As an operator/developer, I want record backend terminal output for diagnostics, so that state bugs can be reproduced from captured bytes. | capture backend records a selected backend for a bounded duration. | CLI | src/main.rs: CaptureAction::Backend; src/capture.rs | Inventoried from code/docs | Drafted | Not Started |  | Not Started | Not Started | P2 | Run a short capture against a harmless shell backend and inspect emitted cap/meta files.
US-CLI-013 | CLI | Promote capture fixture | As a developer, I want promote a capture into replay fixtures, so that regression tests can replay real backend output. | capture promote writes state-replay raw fixtures and manifest entries with scenario metadata. | CLI | src/main.rs: CaptureAction::Promote; src/capture.rs | Inventoried from code/docs | Drafted | Not Started |  | Not Started | Not Started | P2 | Create a tiny .cap fixture and run promote with each required scenario field.
US-CLI-014 | CLI | End-to-end verification | As an operator/releaser, I want run built-in verification probes, so that release smoke checks catch broken daemon/API/backend flows. | verify supports --json, --backend, and --quick; quick skips per-backend and daemon-spawn tests. | CLI | src/main.rs: Commands::Verify; src/verify.rs | Inventoried from code/docs | Drafted | Pass | ERR-001: verify --quick 'instructions' probe always reported claude=false (checked stale .claude/rules/agend.md path that migration deletes). | Done | Pass | P0 | Run agend-terminal verify --quick --json in temp AGEND_HOME. | TEST: After fix, verify --quick reports passed=5 failed=0.
US-CLI-015 | CLI | OS service management | As an operator, I want install, uninstall, and inspect a user service, so that the daemon starts at login and can be supervised by the OS. | service install/uninstall/status are idempotent user-level operations over platform templates. | CLI | src/main.rs: ServiceAction; src/service/mod.rs; src/service/* | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Run service status in the current OS; test install/uninstall in a temp service namespace where possible. | TEST: service status returned not_installed (non-destructive).
US-CLI-016 | CLI | Doctor diagnostics | As an operator, I want diagnose setup, providers, and Telegram topics, so that configuration issues are visible and actionable. | doctor has default checks plus providers and topics subcommands with format/probe/cleanup options. | CLI | src/main.rs: DoctorAction; src/cli.rs; src/bootstrap/doctor*.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Run doctor and doctor providers --format json; run doctor topics --format json with fixture config. | TEST: doctor providers --format json returned structured provider descriptor.
US-CLI-017 | CLI | Shared skills CLI | As an operator, I want add/remove/list/update/install shared skills, so that backend-specific skills stay synchronized from one source. | skills subcommands manage the unified source and install to backend-specific directories. | CLI | src/main.rs: SkillsAction; src/skills.rs; docs/FEATURE-skills.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Use temp skill dir; add/list/update/install/remove and inspect lock file plus per-backend paths. | TEST: skills add/list/install/remove round-tripped; install created per-backend symlinks (.claude/.codex/.opencode/.kiro/.agents).
US-CLI-018 | CLI | Interactive/unattended quickstart | As a new operator, I want generate initial fleet/channel configuration, so that first-run setup is guided or scriptable. | quickstart can run interactively or --unattended/--yes, preserving existing fleet config and sourcing Telegram env when present. | CLI | src/main.rs: Commands::Quickstart; src/quickstart.rs; docs/FEATURE-quickstart.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P0 | Run quickstart --unattended in empty temp AGEND_HOME with and without Telegram env. | TEST: quickstart --unattended created fleet.yaml idempotently in empty AGEND_HOME.
US-CLI-019 | CLI | Bug report generation | As an operator, I want generate a diagnostic report with secrets redacted, so that support can inspect state without exposing credentials. | bugreport collects logs/config and redacts common secret keys/group IDs. | CLI | src/main.rs: Commands::Bugreport; src/bugreport.rs | Inventoried from code/docs | Drafted | Pass | ERR-002 (minor/UX): bugreport wrote bugreport-*.txt into CWD, cluttering whatever dir it was run from. | Done | Pass | P1 | Run bugreport in temp AGEND_HOME containing fake secrets; verify redaction. | TEST: Fixed: bugreport now writes under AGEND_HOME/bugreports; red test failed before impl and passes after fix.
US-CLI-020 | CLI | Shell completions | As an operator, I want generate completions for supported shells, so that the CLI is easier to use interactively. | completions accepts clap-supported shells including bash, zsh, fish, elvish, powershell. | CLI | src/main.rs: Commands::Completions | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P3 | Generate each shell completion and verify output is non-empty. | TEST: completions bash/zsh/fish all produced non-empty scripts.
US-CLI-021 | CLI | Verify push claims | As a reviewer, I want check claims against actual diff, so that PR/review claims are machine-auditable. | verify-push accepts base/head and claim text from stdin or flag, with optional JSON output. | CLI | src/main.rs: Commands::VerifyPush; src/claim_verifier.rs; src/api/handlers/verify_push.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Create a fixture git diff and run true/false claims with --json. | TEST: verify-push --claim-from-stdin --json with known 'deps unchanged' claim returned ok=true and Cargo.lock unchanged.
US-CLI-022 | CLI | Backend hook event bridge | As a backend integration, I want report lifecycle/tool hook events to the daemon, so that shadow state can observe backend actions without blocking them. | hidden hook-event reads JSON from stdin, forwards hook metadata, and exits successfully without context-injecting stdout. | CLI hidden | src/main.rs: Commands::HookEvent; src/api/handlers/hook_event.rs; src/daemon/shadow/* | Inventoried from code/docs | Drafted | Not Started |  | Not Started | Not Started | P2 | Pipe sample hook payloads for Claude/agy and verify daemon evidence mapping in fixtures.
US-MCP-001 | MCP tools | reply — External-channel reply | As an agent, I want reply on the active Telegram/Discord/user channel, so that the operator sees responses in the right place. | Requires daemon API; supports default_action/timeout_secs decision auto-fire. | MCP tool `reply` | src/mcp/tools.rs; src/mcp/handlers/channel.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Call MCP tool `reply` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: reply tool present; channel-bound (no active channel in test) — schema OK.
US-MCP-002 | MCP tools | download_attachment — Attachment download | As an agent, I want download channel media bytes by file_id, so that image/audio/document messages can be processed locally. | Requires daemon API and returns a local file path. | MCP tool `download_attachment` | src/mcp/tools.rs; src/mcp/handlers/channel.rs | Inventoried from code/docs | Drafted | Not Started |  | Not Started | Not Started | P2 | Call MCP tool `download_attachment` with valid and invalid minimal inputs; verify success payload and error shape match schema.
US-MCP-003 | MCP tools | send — Inter-agent send/broadcast | As an agent, I want send task/query/report/update messages to peers, teams, or tags, so that coordination is structured and traceable. | Supports routing fields, task/report metadata, busy gates, task_id enforcement for task dispatch. | MCP tool `send` | src/mcp/tools.rs; src/mcp/handlers/comms.rs; docs/FEATURE-communication.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Call MCP tool `send` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: send returns proper error on self-send (use a different instance).
US-MCP-004 | MCP tools | inbox — Inbox drain/query/ack/clear | As an agent, I want read and acknowledge durable inbox messages, so that offline or busy agents do not lose obligations. | No args drains pending; message_id/thread_id query; action=ack/clear mutate delivery state safely. | MCP tool `inbox` | src/mcp/tools.rs; src/mcp/handlers/comms_inbox.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Call MCP tool `inbox` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: inbox drain returned empty messages list.
US-MCP-005 | MCP tools | list_instances — Instance listing | As an agent, I want inspect live instances, so that routing and availability decisions use current registry state. | Can return compact or verbose rows, with evidence omitted by default. | MCP tool `list_instances` | src/mcp/registry.rs; src/mcp/handlers/instance_queries.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Call MCP tool `list_instances` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: list_instances returned compact registry view.
US-MCP-006 | MCP tools | create_instance — Create agent instance/team | As an operator/agent, I want spawn a backend instance or team, so that work can be distributed dynamically. | Supports backend/model/env/layout/team/worktree branch parameters and persists fleet entries. | MCP tool `create_instance` | src/mcp/tools.rs; src/mcp/handlers/instance_state/spawn.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Call MCP tool `create_instance` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: create_instance spawned w2 (claude) in valid workdir.
US-MCP-007 | MCP tools | delete_instance — Delete instance | As an operator/agent, I want remove an instance and associated lifecycle state, so that stale agents can be cleaned up. | Deletes instance and cascades related team/task cleanup paths. | MCP tool `delete_instance` | src/mcp/registry.rs; src/mcp/handlers/instance_state/lifecycle.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Call MCP tool `delete_instance` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: delete_instance removed w2; list reflected removal.
US-MCP-008 | MCP tools | start_instance — Start stopped instance | As an operator/agent, I want start an existing stopped instance, so that a paused fleet entry can resume. | Starts a stopped instance through daemon lifecycle state. | MCP tool `start_instance` | src/mcp/registry.rs; src/mcp/handlers/instance_state/mod.rs | Inventoried from code/docs | Drafted | Not Started |  | Not Started | Not Started | P2 | Call MCP tool `start_instance` with valid and invalid minimal inputs; verify success payload and error shape match schema.
US-MCP-009 | MCP tools | replace_instance — Replace instance fresh | As an operator/agent, I want replace a stuck instance with a fresh process, so that recovery avoids manual teardown. | Fresh replacement is exposed with reason metadata. | MCP tool `replace_instance` | src/mcp/registry.rs; src/mcp/handlers/instance_state/mod.rs | Inventoried from code/docs | Drafted | Not Started |  | Not Started | Not Started | P2 | Call MCP tool `replace_instance` with valid and invalid minimal inputs; verify success payload and error shape match schema.
US-MCP-010 | MCP tools | restart_instance — Restart instance | As an operator/agent, I want restart in resume or fresh mode, so that sessions recover while preserving context when possible. | fresh refuses dirty worktrees unless force=true; resume preserves conversation state. | MCP tool `restart_instance` | src/mcp/tools.rs; src/mcp/handlers/instance_state/mod.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Call MCP tool `restart_instance` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: restart_instance resume mode respawned w2.
US-MCP-011 | MCP tools | interrupt — Interrupt instance | As an operator/agent, I want send ESC to an agent PTY, so that a running model turn can be stopped without killing the session. | Can optionally return a pane snapshot after interrupt. | MCP tool `interrupt` | src/mcp/tools.rs; src/mcp/handlers/instance.rs | Inventoried from code/docs | Drafted | Not Started |  | Not Started | Not Started | P2 | Call MCP tool `interrupt` with valid and invalid minimal inputs; verify success payload and error shape match schema.
US-MCP-012 | MCP tools | set_display_name — Set display name | As an agent, I want change my visible name, so that TUI/channel users can identify panes. | Sets or clears display metadata for the caller. | MCP tool `set_display_name` | src/mcp/tools.rs; src/mcp/handlers/instance_metadata.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Call MCP tool `set_display_name` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: set_display_name set display metadata.
US-MCP-013 | MCP tools | set_description — Set description | As an agent, I want set a short visible description, so that the operator can see current role/context. | Sets or clears per-instance description metadata. | MCP tool `set_description` | src/mcp/tools.rs; src/mcp/handlers/instance_metadata.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Call MCP tool `set_description` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: set_description set instance description.
US-MCP-014 | MCP tools | set_waiting_on — Declare waiting/blocker | As an agent, I want publish what I am waiting for, so that fleet status makes blockers visible. | Sets an auto-staling waiting_on condition. | MCP tool `set_waiting_on` | src/mcp/tools.rs; src/mcp/handlers/instance_metadata.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Call MCP tool `set_waiting_on` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: set_waiting_on set + cleared the waiting condition.
US-MCP-015 | MCP tools | move_pane — Move pane between tabs | As an operator/agent, I want move an instance pane into a target tab, so that TUI layout can be reorganized without restarting agents. | Preserves scrollback and PTY state while moving pane. | MCP tool `move_pane` | src/mcp/tools.rs; src/mcp/handlers/instance.rs | Inventoried from code/docs | Drafted | Not Started |  | Not Started | Not Started | P2 | Call MCP tool `move_pane` with valid and invalid minimal inputs; verify success payload and error shape match schema.
US-MCP-016 | MCP tools | pane_snapshot — Read pane scrollback | As an agent, I want capture visible or full pane text, so that review/diagnostic agents can inspect peer state. | Supports bounded lines and to_file=true for large captures. | MCP tool `pane_snapshot` | src/mcp/tools.rs; src/mcp/handlers/instance.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Call MCP tool `pane_snapshot` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: pane_snapshot returned live PTY scrollback text.
US-MCP-017 | MCP tools | tui_screenshot — Capture TUI screenshot | As an agent, I want capture the current TUI as SVG, so that visual layout issues can be reviewed. | Works in TUI mode and returns SVG content. | MCP tool `tui_screenshot` | src/mcp/tools.rs; src/mcp/handlers/dispatch.rs | Inventoried from code/docs | Drafted | Not Started |  | Not Started | Not Started | P2 | Call MCP tool `tui_screenshot` with valid and invalid minimal inputs; verify success payload and error shape match schema.
US-MCP-018 | MCP tools | decision — Decision records | As an agent/operator, I want post/list/update/answer decision records, so that scope choices and operator questions are durable. | Actions: post, list, update, answer; supports pending questions/options/free-text. | MCP tool `decision` | src/mcp/tools.rs; src/decisions.rs; docs/FEATURE-decisions.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Call MCP tool `decision` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: decision post/list round-tripped a project-scoped decision.
US-MCP-019 | MCP tools | task — Task board | As an agent/operator, I want create/list/get/claim/done/update/sweep/health tasks, so that all work is tracked in a shared event-sourced board. | Supports metadata and terse/full projections with event-sourced lifecycle. | MCP tool `task` | src/mcp/tools.rs; src/tasks/*; src/task_events.rs; docs/FEATURE-task-board.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Call MCP tool `task` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: task create/list/health all returned valid event-sourced records.
US-MCP-020 | MCP tools | task_sweep_config — Task auto-close sweep config | As an operator, I want configure PR-merge task auto-close sweep, so that merged PRs can close task records automatically. | Configures repository sweep, dry-run, and pause state. | MCP tool `task_sweep_config` | src/mcp/tools.rs; src/daemon/task_sweep.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Call MCP tool `task_sweep_config` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: task_sweep_config returned config (after mode active).
US-MCP-021 | MCP tools | restart_daemon — Daemon restart | As an operator/agent, I want request a graceful daemon restart, so that binary refreshes can hand off without external supervision. | Self-respawns when supported; app mode reports actionable failure. | MCP tool `restart_daemon` | src/mcp/tools.rs; src/daemon/restart.rs | Inventoried from code/docs | Drafted | Not Started |  | Not Started | Not Started | P2 | Call MCP tool `restart_daemon` with valid and invalid minimal inputs; verify success payload and error shape match schema.
US-MCP-022 | MCP tools | team — Team CRUD | As an operator/agent, I want create/delete/list/update teams, so that agents can be grouped with orchestrator routing. | Writes fleet.yaml, enforces one-agent-one-team, stale/degraded projections. | MCP tool `team` | src/mcp/tools.rs; src/teams.rs; docs/FEATURE-teams.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Call MCP tool `team` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: team list returned empty team set.
US-MCP-023 | MCP tools | schedule — Schedule CRUD | As an operator/agent, I want create/list/update/delete timed messages, so that routine prompts can fire automatically. | Supports cron/one-shot triggers, time zones, and until_success strategy. | MCP tool `schedule` | src/mcp/tools.rs; src/schedules.rs; docs/FEATURE-schedules.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Call MCP tool `schedule` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: schedule create/list round-tripped a cron schedule (after mode active).
US-MCP-024 | MCP tools | deployment — Deployment templates | As an operator, I want deploy/teardown/list template deployments, so that repeatable multi-instance environments can be started. | Deployment templates create named instance sets and worktrees. | MCP tool `deployment` | src/mcp/tools.rs; src/deployments.rs; docs/FEATURE-schedules.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Call MCP tool `deployment` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: deployment list returned empty deployments.
US-MCP-025 | MCP tools | ephemeral — Ephemeral workers | As an agent/operator, I want spawn/list/reap short-lived workers, so that bounded one-shot helper work can run outside managed fleet bookkeeping. | Supports TTL, backend, model, prompt, and workflow_id fields. | MCP tool `ephemeral` | src/mcp/tools.rs; src/ephemeral_driver.rs; src/ephemeral_tracking.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Call MCP tool `ephemeral` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: ephemeral list returned worker pool state (after mode active).
US-MCP-026 | MCP tools | ci — CI watch | As an agent/operator, I want watch/unwatch/status CI for branches, so that PR readiness can notify agents automatically. | Supports GitHub/Bitbucket Cloud provider metadata, polling interval, next_after_ci, review class. | MCP tool `ci` | src/mcp/tools.rs; src/daemon/ci_watch/*; docs/FEATURE-ci-watch.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Call MCP tool `ci` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: ci status returned empty watch list.
US-MCP-027 | MCP tools | health — Health report/clear | As an agent, I want report or clear blocked health state, so that fleet health dashboards show rate limits/quota/operator waits. | Actions: report and clear; report has reason and retry_after_secs. | MCP tool `health` | src/mcp/tools.rs; src/health.rs; docs/FEATURE-health.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Call MCP tool `health` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: health report set rate_limit reason.
US-MCP-028 | MCP tools | watchdog — Fleet idle watchdog | As an operator/agent, I want snooze/resume/status/ack idle alerts, so that idle fleet notifications can be controlled. | Snooze clamps duration; ack suppresses until post-ack activity. | MCP tool `watchdog` | src/mcp/tools.rs; src/daemon/idle_watchdog.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Call MCP tool `watchdog` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: watchdog status returned snooze/ack state.
US-MCP-029 | MCP tools | config — Runtime config | As an operator/agent, I want get/set/list mutable daemon configuration, so that thresholds and UI flags can change without rebuilding. | Validates known keys and writes runtime-config.json. | MCP tool `config` | src/mcp/tools.rs; src/runtime_config.rs; docs/FEATURE-configuration.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Call MCP tool `config` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: config get/list returned typed runtime config keys.
US-MCP-030 | MCP tools | repo — Repo/worktree operations | As an agent/operator, I want checkout/release/cleanup/merge repository worktrees, so that work happens in isolated daemon-managed branches. | Supports checkout bind=true, cleanup init commits/merged branches, and PR merge. | MCP tool `repo` | src/mcp/tools.rs; src/mcp/handlers/ci/*; docs/FEATURE-worktree.md | Inventoried from code/docs | Drafted | Fail | ERR-003 (env-only, not a product defect): repo checkout bind=true denied by agend-git shim (#2234 canonical-rooted mutate guard) because the test daemon ran rooted in the canonical repo. Expected guard behaviour. | N/A | Pass | P1 | Call MCP tool `repo` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: Re-confirmed as intended safety guard; not a code bug. Schema + handler path exercised.
US-MCP-031 | MCP tools | bind_self — Bind caller to worktree | As an agent, I want bind my instance to a branch worktree, so that I can safely do repository work outside initial dispatch. | Rejects protected branches; supports repository_path and rebase_mode. | MCP tool `bind_self` | src/mcp/tools.rs; src/binding.rs; src/worktree_pool.rs | Inventoried from code/docs | Drafted | Not Started |  | Not Started | Not Started | P2 | Call MCP tool `bind_self` with valid and invalid minimal inputs; verify success payload and error shape match schema.
US-MCP-032 | MCP tools | release_worktree — Release bound worktree | As an agent/operator, I want soft-release a daemon-managed worktree, so that worktree ownership and cleanup state are clear. | Clears binding and marks .agend-managed release metadata; dry_run previews. | MCP tool `release_worktree` | src/mcp/tools.rs; src/worktree_pool.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Call MCP tool `release_worktree` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: release_worktree idempotently reported released state.
US-MCP-033 | MCP tools | force_release_worktree — Emergency worktree release | As an operator, I want force clean stale daemon-managed worktrees, so that dangling leases can be recovered safely. | Requires instance/branch and refuses paths outside daemon pool. | MCP tool `force_release_worktree` | src/mcp/tools.rs; src/mcp/handlers/force_release/* | Inventoried from code/docs | Drafted | Not Started |  | Not Started | Not Started | P2 | Call MCP tool `force_release_worktree` with valid and invalid minimal inputs; verify success payload and error shape match schema.
US-MCP-034 | MCP tools | binding_state — Binding inspection | As an agent/operator, I want inspect binding/worktree/CI watch state, so that agents can find their authoritative worktree. | Reports binding.json, worktree marker, watches, bind-in-flight, cross-branch holders. | MCP tool `binding_state` | src/mcp/tools.rs; src/mcp/handlers/binding_state.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Call MCP tool `binding_state` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: binding_state returned full structured bind report.
US-MCP-035 | MCP tools | gc_dry_run — Worktree GC preview | As an operator, I want preview daemon-managed worktree GC candidates, so that cleanup can be audited before deletion. | Lists released past-grace candidates without mutation. | MCP tool `gc_dry_run` | src/mcp/tools.rs; src/worktree_pool/gc.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Call MCP tool `gc_dry_run` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: gc_dry_run listed 0 candidates without mutation.
US-MCP-036 | MCP tools | tokens — Token/cost summary | As an operator, I want summarize estimated Claude/Codex token usage, so that fleet cost/context consumption can be monitored. | Supports summary/by_instance and instance/task attribution groups. | MCP tool `tokens` | src/mcp/tools.rs; src/token_cost.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Call MCP tool `tokens` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: tokens summary returned backend cost summary.
US-MCP-037 | MCP tools | mode — Read operator mode | As an agent, I want read active/away/sleep operator mode, so that agents can back off when operator is unavailable. | MCP mode is read-only and returns delegate/scope. | MCP tool `mode` | src/mcp/tools.rs; src/operator_mode.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Call MCP tool `mode` with valid and invalid minimal inputs; verify success payload and error shape match schema. | TEST: mode get returned operator mode (read-only).
US-TUI-001 | TUI | Tab management shortcuts | As an operator, I want create, switch, list, close, and rename tabs with Ctrl+B shortcuts, so that I can organize work without leaving the TUI. | Ctrl+B c/n/p/l/0-9/&/,/w dispatch to tab actions; repeated navigation keys keep prefix active. | TUI | src/keybinds.rs; src/layout/tab.rs; docs/FEATURE-tui.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Drive key events for each tab shortcut and assert layout/session state. | TEST: cargo test --bin agend-terminal keybinds + layout:: passed.
US-TUI-002 | TUI | Pane split/focus/zoom/move | As an operator, I want split panes, resize, move, and zoom them, so that I can compare agents side-by-side. | Ctrl+B quote/percent/o/arrows/Alt-arrows/HJKL/x/z/space/./!/@ map to pane layout actions. | TUI | src/keybinds.rs; src/layout/*; src/app/tui_events.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Drive key events and inspect layout tree invariants after each action. | TEST: layout::, app::dispatch, and keybinds tests passed for split/focus/zoom/move actions.
US-TUI-003 | TUI | Scroll mode | As an operator, I want scroll terminal history by keyboard and mouse, so that I can inspect prior output. | Ctrl+B [ enters scroll mode; j/k/arrows/PgUp/PgDn scroll; q/Esc exits. | TUI | src/keybinds.rs; src/vterm.rs; docs/FEATURE-tui.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Populate long PTY output, enter scroll mode, verify offset changes and exits. | TEST: app::tui_events and keybinds tests passed for scroll-mode dispatch.
US-TUI-004 | TUI | Panels and overlays | As an operator, I want open decisions, tasks, status, monitor, fleet, help, scratch, and command palette overlays, so that fleet control and diagnostics are discoverable. | Ctrl+B D/T/s/m/f/?/~/colon/d map to overlays/detach; scratch shell closes with Esc. | TUI | src/keybinds.rs; src/app/overlay.rs; src/render/overlay.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Open and close each overlay in a fixture TUI loop. | TEST: app::overlay and app::tui_events tests passed for panels/overlays.
US-TUI-005 | TUI | Mouse controls | As an operator, I want click/drag panes, tabs, splits, and selection, so that layout manipulation is direct. | Mouse module handles pane focus, tab switching, split resize, pane swap/move, scrolling, and Shift+Drag selection. | TUI | src/app/mouse.rs; src/mouse_forward.rs; docs/FEATURE-tui.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Replay crossterm mouse events for click/drag/scroll and assert layout/selection. | TEST: cargo test --bin agend-terminal app::mouse passed (27 tests).
US-TUI-006 | TUI | Copy/select and image paste | As an operator, I want copy selected text and paste clipboard images into agents, so that rich context can be sent to backends. | Runtime copy_on_select can be toggled; Ctrl+B i writes an [AGEND-IMAGE-PASTE] marker with a captured image path. | TUI | src/keybinds.rs; src/image_paste.rs; src/runtime_config.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Toggle copy_on_select and paste a fixture image from clipboard abstraction. | TEST: keybinds and image_paste tests passed.
US-TUI-007 | TUI | Command palette | As an operator, I want run spawn/split/layout/kill/restart/send/broadcast/status commands, so that advanced actions are available by name. | Command palette specs provide keyword completion and argument sources for config keys/subcommands/free text. | TUI | src/app/commands.rs; docs/FEATURE-tui.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Invoke each command with valid/invalid arguments and verify visible errors/actions. | TEST: cargo test --bin agend-terminal app::commands passed (16 tests).
US-TUI-008 | TUI | Session persistence and restoration | As an operator, I want restore tabs, panes, proportions, active tab, and names, so that my TUI workspace survives restarts. | Session module persists layout state and restoration reconciles panes with live registry. | TUI | src/app/session.rs; src/layout/*; docs/FEATURE-tui.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Save a multi-tab session, restart TUI in temp state, verify restoration. | TEST: cargo test --bin agend-terminal app::session passed (12 tests).
US-SYS-001 | System / infrastructure | Core daemon tick loop | As an operator, I want the daemon to orchestrate periodic subsystems, so that state, cleanup, notifications, and supervision continue without manual polling. | Daemon ticker runs per-tick coordinators for schedule checks, CI polling, snapshots, GC, watchdogs, recovery, and notifications. | Daemon | src/daemon/mod.rs; src/daemon/ticker.rs; src/daemon/per_tick/* | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P0 | Run daemon with temp AGEND_HOME and assert expected per-tick side effects with reduced intervals. | TEST: daemon::ticker, daemon::per_tick, and daemon::cron_tick tests passed.
US-SYS-002 | System / infrastructure | Agent supervision and crash recovery | As an operator, I want agents to be monitored and restarted when policy allows, so that temporary backend crashes do not permanently break the fleet. | Supervisor detects exits/crashes, applies retry and crash-respawn logic, and surfaces terminal failures. | Daemon | src/daemon/supervisor.rs; src/daemon/crash_respawn.rs; src/instance_monitor.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P0 | Spawn a short-lived fixture backend and verify recovery/failed-state transitions. | TEST: daemon::supervisor and daemon::crash_respawn tests passed.
US-SYS-003 | System / infrastructure | Backend presets and resume modes | As an operator, I want use Claude, Codex, Kiro, OpenCode, agy/Antigravity, and raw shell backends, so that different AI CLIs can be managed uniformly. | Backend enum parses preset/raw commands, formats model args, emits spawn flags, and supports backend-specific resume/dismiss behavior. | Backend | src/backend.rs; src/backend_profile.rs; docs/PROVIDERS.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Unit-test parse/preset/spawn args for all supported backends. | TEST: backend tests passed (125 passed, 3 ignored).
US-SYS-004 | System / infrastructure | Agent state and behavioral inference | As an operator, I want see whether agents are idle, thinking, using tools, hung, or rate-limited, so that routing and recovery decisions are based on observed state. | State tracker combines terminal patterns, heartbeat/shadow evidence, and silence thresholds. | Daemon/TUI | src/state/*; src/behavioral.rs; src/daemon/shadow/* | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Replay state fixtures and assert classifications. | TEST: state:: and behavioral tests passed.
US-SYS-005 | System / infrastructure | Telegram/Discord channel abstraction | As an operator, I want bind external conversations to agents and fleet events, so that messages round-trip through topics/threads. | Channel trait supports send/edit/delete/binding/topic/poll; Telegram and Discord adapters implement platform-specific behavior. | Channels | src/channel/*; docs/FEATURE-channels.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Use mocked channel adapters to verify inbound/outbound/dedup/topic flows. | TEST: channel:: and channel::telegram tests passed.
US-SYS-006 | System / infrastructure | Notification queue/dedup/gates | As an operator, I want avoid duplicate or unauthorized notifications, so that external channels stay readable and safe. | Notification queue, channel dedup, outbound caps, and notification gates filter repeated or forbidden sends. | Channels | src/notification_queue.rs; src/channel/dedup.rs; src/channel/caps.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Enqueue duplicate notifications and verify one delivered; test capability denial. | TEST: notification_queue tests passed.
US-SYS-007 | System / infrastructure | Fleet YAML and instance resolution | As an operator, I want configure instances, teams, roles, env, models, skills, repos, and topics, so that daemon startup is reproducible. | Fleet config merge preserves operator fields, daemon-managed fields, source_repo, and team metadata. | Config | src/fleet/*; src/bootstrap/agent_resolve.rs; docs/FEATURE-configuration.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P0 | Load/normalize fixture fleet.yaml variants and assert resolved instances. | TEST: fleet:: tests passed.
US-SYS-008 | System / infrastructure | Runtime mutable config | As an operator, I want change thresholds and UI flags live, so that daemon behavior can be tuned without restart. | Runtime config exposes known keys with typed defaults and parse validation. | Config/MCP | src/runtime_config.rs; src/mcp/handlers/dispatch.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | MCP config get/list/set for every key and invalid values. | TEST: runtime_config tests passed.
US-SYS-009 | System / infrastructure | Backend MCP config generation | As an operator, I want derive per-backend MCP and hook settings, so that agents receive the right tools without touching global config. | Generator writes backend-specific config under working dirs and backs up malformed JSON. | Config | src/mcp_config.rs; docs/FEATURE-configuration.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Generate configs for each backend in temp workdirs and inspect paths/content. | TEST: mcp_config tests passed.
US-SYS-010 | System / infrastructure | Daemon-managed worktree pool | As a developer agent, I want work in isolated branch worktrees with binding metadata, so that parallel agents do not corrupt the canonical checkout. | Worktree pool leases validated branches, writes .agend-managed and binding.json, and releases/GCs safely. | Git/worktree | src/worktree.rs; src/worktree_pool.rs; src/binding.rs; docs/FEATURE-worktree.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P0 | Use a temp git repo to checkout/bind/release/gc dry-run branches. | TEST: worktree and binding tests passed.
US-SYS-011 | System / infrastructure | Git shim and commit/push safeguards | As a developer agent, I want have git operations routed and guarded inside managed worktrees, so that audit trailers and safety deny rules are consistently applied. | agend-git handles protected refs, DCO/signoff, claim verification hooks, and worktree redirect constraints. | Git helper | src/bin/agend-git.rs; docs/GIT-BEHAVIOR.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P0 | Run fixture git commands through shim for allowed/denied cases. | TEST: cargo test --bin agend-git passed (85 tests).
US-SYS-012 | System / infrastructure | PR state and CI monitoring | As a reviewer/orchestrator, I want monitor checks, conflicts, PR merge state, and ready gates, so that merge workflows proceed only with current evidence. | CI pollers and PR scanners track checks, conflicts, verdict buffers, remote GC, and ready gates. | Daemon/MCP | src/daemon/ci_watch/*; src/daemon/pr_state/* | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P0 | Mock provider responses for pending/fail/pass/conflict/merged PR states. | TEST: daemon::ci_watch and daemon::pr_state tests passed.
US-SYS-013 | System / infrastructure | Event-sourced task board | As an agent, I want track work through append-only events, so that work state remains auditable and recoverable. | Task events replay archive+hot logs, strict schema, ACLs, migration, sweep, health, and metadata. | MCP/TUI | src/task_events.rs; src/tasks/*; docs/FEATURE-task-board.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P0 | Create/claim/update/done/sweep fixture board and replay from disk. | TEST: tasks:: and task_events tests passed.
US-SYS-014 | System / infrastructure | Decision persistence | As an operator/agent, I want record scope decisions and operator answers, so that future agents can understand why choices were made. | Decision store supports post/list/update/answer/supersede/archive and TTL. | MCP/TUI | src/decisions.rs; docs/FEATURE-decisions.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Post/list/update/supersede/answer with ACL and free-text variants. | TEST: decision MCP smoke passed.
US-SYS-015 | System / infrastructure | Schedules and deployments | As an operator, I want run cron/one-shot tasks and deploy template fleets, so that recurring work and batch environments are automated. | Schedule store validates cron/time zones/until_success; deployments create/delete/list template groups. | MCP | src/schedules.rs; src/deployments.rs; docs/FEATURE-schedules.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Create one-shot and cron fixtures, tick scheduler, deploy/teardown a template. | TEST: schedules and deployments tests passed.
US-SYS-016 | System / infrastructure | Retention and garbage collection | As an operator, I want clean stale worktrees, decisions, pending dispatches, branches, inbox, and run dirs, so that state does not grow forever. | Boot/per-tick retention modules sweep stale data with dry-run/safety gates. | Daemon/Admin/MCP | src/daemon/retention/*; src/daemon/boot_sweep.rs; src/worktree_pool/gc.rs; src/branch_sweep.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P2 | Seed stale fixture state and verify dry-run before apply paths. | TEST: daemon::retention tests passed.
US-SYS-017 | System / infrastructure | Auth cookies and integrity checks | As an operator, I want protect local daemon APIs and signed state, so that accidental or malicious local injection is constrained. | Auth cookie and HMAC integrity modules issue, verify, and reject malformed/tampered values. | Daemon/API | src/auth_cookie.rs; src/config_integrity.rs; src/integrity_core.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P0 | Run unit tests for cookie round-trip, wrong cookie, malformed tag, tamper cases. | TEST: auth_cookie and config_integrity tests passed.
US-SYS-018 | System / infrastructure | Internal API server and request dedup | As a CLI/MCP client, I want call daemon methods over the local API, so that CLI/TUI/MCP surfaces share one consistent control plane. | API handlers route instance, messaging, team, query, hook, verify-push, and MCP proxy methods with request dedup. | API | src/api/*; src/ipc.rs; src/framing.rs | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P0 | Start API fixture and call representative methods with duplicate request IDs. | TEST: api::tests and api::request_dedup tests passed.
US-SYS-019 | System / infrastructure | MCP stdio bridge | As an agent backend, I want speak MCP over stdio to the daemon, so that backend tools work without direct daemon API implementation. | agend-mcp-bridge connects MCP tool calls to daemon handlers and handles bootstrap config. | MCP binary | src/bin/agend-mcp-bridge.rs; src/bridge_client.rs; src/mcp/* | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P0 | Run bridge with initialize/tools/list/call fixture messages. | TEST: agend-mcp-bridge tools/list returned all 37 tools; tools/call round-tripped.
US-SYS-020 | System / infrastructure | Diagnostics and evidence capture | As an operator/reviewer, I want collect bugreports, captures, screenshots, pane snapshots, logs, and thread dumps, so that bugs can be reproduced with sufficient evidence. | Diagnostics modules redact secrets, capture terminal bytes, render screenshots, rotate logs, and expose snapshots. | CLI/MCP/TUI | src/bugreport.rs; src/capture.rs; src/screenshot.rs; src/logging.rs; src/thread_census.rs; docs/FEATURE-diagnostics.md | Inventoried from code/docs | Drafted | Pass |  | N/A | Pass | P1 | Run diagnostics commands in temp state and inspect redaction/rotation/output shape. | TEST: bugreport red/green tests passed; diagnostics command smoke passed.
US-SYS-021 | System / infrastructure | System tray resident app | As an operator, I want run a tray/menu app when the tray feature is enabled, so that daemon control can live in the OS menu bar. | Tray feature gates tray-icon/tao dependencies and provides config/icon/menu/autostart/terminal launch modules. | Feature-gated CLI | Cargo.toml feature tray; src/tray/*; docs/USAGE.md | Inventoried from code/docs | Drafted | Not Started |  | Not Started | Not Started | P3 | Build with --features tray and smoke tray config/menu functions where platform allows.
US-SYS-022 | System / infrastructure | Discord channel feature flag | As an operator, I want enable Discord support only when requested, so that default builds stay lean while Discord integration remains available. | Cargo feature discord gates twilight dependencies and DiscordChannel implementation. | Feature-gated channel | Cargo.toml feature discord; src/channel/discord.rs | Inventoried from code/docs | Drafted | Not Started |  | Not Started | Not Started | P3 | cargo check --features discord and mocked Discord adapter tests.

## Error Log
Error ID | Linked Story ID | Date Found | Test Step | Observed Error | Severity | Status | Fix Notes | Retest Evidence
ERR-001 | US-CLI-014 | 2026-06-29 | agend-terminal verify --quick --json | 'instructions' probe always reported claude=false: test_instructions() checked .claude/rules/agend.md, but generate() now writes .claude/agend.md and migrate_claude_old_rules_file() deletes the rules/ path. The probe could never pass. | Medium (logistical / false-negative self-test) | Fixed | src/verify.rs: point claude_path at .claude/agend.md (canonical preset path). | Rebuilt release binary; verify --quick --json -> passed=5 failed=0; instructions probe now Pass.
ERR-002 | US-CLI-019 | 2026-06-29 | agend-terminal bugreport | bugreport writes bugreport-<ts>.txt into the current working directory (std::env::current_dir), not $AGEND_HOME, so it litters whatever dir the operator runs it from (e.g. a git worktree). | Low (UX) | Fixed | src/bugreport.rs now writes to AGEND_HOME/bugreports/ and creates that directory. English/zh-TW CLI + diagnostics docs updated. | Red test-only commit failed as expected (wrote into CWD); post-fix cargo test --test cli_smoke bugreport_writes_with_valid_home passed and direct smoke wrote only under AGEND_HOME/bugreports/.
ERR-003 | US-MCP-030 | 2026-06-29 | MCP repo action=checkout bind=true (test daemon rooted in canonical repo) | agend-git shim DENIED worktree add (#2234 canonical-rooted mutate guard). This is the intended safety behaviour when invoked from a canonical-rooted daemon, NOT a product defect. | Info (expected guard) | Won't Fix | Behaving as designed; documented so future audits don't mis-file it as a bug. | Re-confirmed guard fires deterministically with the documented remediation message.

## Test Runs
Run ID | Date | Story ID | Tester | Command / Interaction | Expected | Actual | Result | Evidence Path
RUN-001 | 2026-06-29 | US-CLI-001/005/007/008 | fugu-0acdd8 | start (service) -> list -> inject -> kill -> stop in isolated AGEND_HOME | Daemon lifecycle + agent control work | All worked; marker file written by injected command | Pass | /tmp/agend-test.* daemon logs
RUN-002 | 2026-06-29 | US-CLI-014 | fugu-0acdd8 | verify --quick --json (pre-fix) | All 5 probes pass | instructions probe failed (claude=false) | Fail | verify JSON output
RUN-003 | 2026-06-29 | US-CLI-020/015/016/018/019 | fugu-0acdd8 | completions/service status/doctor providers/quickstart/bugreport | Each command produces expected output | All produced expected output; bugreport path UX noted | Pass | console capture
RUN-004 | 2026-06-29 | US-MCP-* (33 tools) | fugu-0acdd8 | agend-mcp-bridge tools/list + tools/call for each MCP tool | Tools dispatch and return valid payloads / proper errors | 37 tools listed; all exercised tools returned valid results (authority gating respected) | Pass | bridge stdio capture
RUN-005 | 2026-06-29 | US-CLI-014 | fugu-0acdd8 | verify --quick --json (post-fix, rebuilt release) | instructions probe passes | passed=5 failed=0; instructions=Pass | Pass | verify JSON output
RUN-006 | 2026-06-29 | US-CLI-017 | fugu-0acdd8 | skills add/list/install/remove in isolated AGEND_HOME | Skill round-trips + per-backend install | Symlinks created at 5 backend paths; remove idempotent | Pass | console capture
RUN-007 | 2026-06-29 | US-CLI-010 | fugu-0acdd8 | admin cleanup-branches (dry-run) against source repo | Preview-only, no deletions | 24 branches evaluated, 0 deleted (dry-run); audit log written then cleaned | Pass | console capture
RUN-008 | 2026-06-29 | US-CLI-019 | fugu-0acdd8 | bugreport red/green regression | Bugreport writes under AGEND_HOME/bugreports and not CWD | test-only commit failed; implementation commit passed cli_smoke + bin bugreport tests | Pass | cargo test --test cli_smoke bugreport_writes_with_valid_home; cargo test --bin agend-terminal bugreport
RUN-009 | 2026-06-29 | US-TUI-001..008 | fugu-0acdd8 | TUI unit/dispatcher tests | Keyboard, mouse, overlay, command, layout, session, image-paste behaviours pass | keybinds 19; commands 16; mouse 27; session 12; layout 59; tui_events 13; overlay 14; image_paste 9 all passed | Pass | cargo test --bin agend-terminal <filters>
RUN-010 | 2026-06-29 | US-DOC/SYS channel/config/worktree/task/daemon rows | fugu-0acdd8 | Subsystem cargo-test batches | Subsystem invariants pass | channel 195; ci_watch 226; pr_state 91; worktree 238; binding 53; tasks 163; task_events 49; schedules 33; deployments 55; teams 34; health 53; daemon/per_tick/ticker/supervisor batches passed | Pass | cargo test --bin agend-terminal <filters>
RUN-011 | 2026-06-29 | US-SYS-011 | fugu-0acdd8 | agend-git safety tests | Git shim safeguards pass | 85 passed | Pass | cargo test --bin agend-git
RUN-012 | 2026-06-29 | US-CLI-006 | fugu-0acdd8 | connect bad backend red/green regression + positive connect smoke | Failed backend spawn must not leave stale external agent; valid backend exits cleanly | red test failed with badext listed; post-fix test passed; /usr/bin/true connect exited 0 | Pass | cargo test --test cli_smoke connect_failed_spawn_deregisters_external_agent; manual isolated daemon smoke
RUN-013 | 2026-06-29 | US-CLI-021 | fugu-0acdd8 | verify-push --claim-from-stdin --json | Known claim grammar verifies against diff | deps unchanged -> ok=true, Cargo.lock unchanged | Pass | target/debug/agend-terminal verify-push --base origin/main --head HEAD --claim-from-stdin --json

## Sources
Source Type | Path | Reason Used
Feature docs | docs/FEATURE-*.md | Documented user-facing feature surfaces and workflows
CLI source | src/main.rs | Clap command and subcommand definitions
MCP schema | src/mcp/tools.rs; src/mcp/registry.rs | Exposed tool names, descriptions, and action enums
TUI/keybindings | src/keybinds.rs; src/app/*; src/layout/*; src/render/* | Interactive user behaviours
Architecture map | docs/project-feature-groups.md | Subsystem coverage cross-check
Core modules | src/daemon/*; src/tasks/*; src/worktree*; src/channel/*; src/fleet/* | Expected behaviours for subsystem-level stories

## Legend
Column | Meaning
Inventory Status | Whether the feature has been identified from source evidence.
Story Status | Whether the user story/expected behaviour is drafted or needs refinement.
Test Status | Not Started / In Progress / Pass / Fail / Blocked.
Observed Errors | Concrete error(s) found during story testing.
Fix Status | Not Started / Needs Fix / In Progress / Done / N/A.
Retest Status | Not Started / Pass / Fail / Blocked after the fix loop.
Priority | P0 critical flow, P1 core workflow, P2 important, P3 nice-to-have or feature-gated.